## Sheet1
Task Name | Duration | Start | Finish
Adding improvements to the milestone of STEPS | 3 day | Mon 11/20/17 | Wed 11/22/17
Revision of Controllers of each Admins | 1 day | Mon 11/27/17 | Mon 11/27/17
Revised names of Class Diagram | 1 day | Wed 11/29/2017 | Thur 11/30/2017
Addition of feature: Freshmen Enrollment |  | Sun 12/17/17
Revision of ER Diagram |  | Sun 12/17/17
Few Additions in Class Diagram |  | Sun 12/17/17
Addition of Freshmen |  | Sun 12/17/17